## Slide 1: NASA EVA Gamification - Phase 2
Prepared By:
Laura Addiego
Samia Alam
Kelli Corey
Charles Milk
Adeola Odusola
Hung Pham
Notes: Hello Dr. Brown, Thank you for taking the time to go over our NASA EVA gamification presentation. We are here to present phase 2 of the NASA EVA Gamification Project plan.

## Slide 2: Project Overview
NASA EVA MediaWiki supports NASA Extravehicular Activity (EVA) group’s knowledge management processes.
The ultimate goal is to gamify the NASA EVA Wikimedia.
Phase 1 involved user profile creation, email verification, and database configuration.
Phase 2 will add different elements of gamification: personality types, simple point system, badges, and adding a leaderboard.
Notes: Our project is based on a need raised by NASA Johnson Space Center. NASA EVA Wiki is used to support the Extravehicular Activity (EVA) group’s knowledge management processes. It is a private wiki which is used to support various operations at NASA International Space Station.
The ultimate goal of the project is to gamify the NASA EVA MediaWiki. Gamification is the process of integrating gaming mechanics into existing product or process to increase user participation and engagement. Phase one of the project which included user profile creation, email verification, and database setup work has already been completed. Phase two is the continuation of the NASA wiki gamification project after the successful completion of phase one. Phase two will focus on adding different elements of gamification to the existing product. The elements will include adding different personality types, simple point system, badges, and adding a leaderboard.

## Slide 3: Project Stakeholders
Liaison
Daren Welsh, EVA Instructor and Flight Controller
Sponsor
Extravehicular Activity (EVA), Johnson Space Center, NASA
Project Manager
Dr. Michael Brown
Project Team Members
Laura Addiego
Samia Alam
Kelli Corey
Charles Milk
Adeola Odusola
Hung Pham
Notes: Our Project is sponsored by Johnson Space Center, NASA. More specifically, the Extra-vehicular Activity sector from NASA is our focused client. Daren Welsh who is a NASA EVA instructor and flight controller is the Liaison for our project. Other stakeholders include the project manager Dr. Michael Brown, and all team members of the phase 2 of the project.

## Slide 4: Software Platform
MediaWiki (1.27.4)
Meza install bundle (https://github.com/enterprisemediawik)
PHP (5.6)
MariaDB/MySQL (5.5.59)
Notes: The project will continue to use the same platform that was used by the previous team.

## Slide 5: Team Roles
Customer Management Lead - Charles Milk
Development Lead - Hung Pham
Quality Assurance Lead - Samia Alam
Database Lead - Laura Addiego
Documentation Lead - Adeola Odusola
Project Management Lead - Kelli Corey

## Slide 6: Scope
Continue work on the NASA EVA wiki project from Phase 1
Build an extension consolidating infrastructure allowing system to:
  Manage the point measurement system
  Manage badge rewards system
  Manage leaderboard ranks system.
Manage many different personality types within a unified system.
Scalable system to allow for other personality types like socialites and explorers.
Notes: The scope of phase two project is the continuation of the work on the wiki project from the previous team.
The primary focus of this phase two project will build an extension that provides a consolidated infrastructure allowing for adding different elements and approaches to gamification.
Through this single extension, many different personality types could be addressed with a unified system.
It will include simple point measurement, badge rewards system, and leaderboard ranks system, but the system will be scalable to allow for other personality types like socialites and explorers.

## Slide 7: Communication
Internal
Channel | Tool | Description/Purpose | Formality | Type | Frequency
Instant messaging | Slack | For quick communication and general purposes | Informal | Written | As needed
Email | Personal email | To distribute weekly meeting invitation | Informal | Written | Weekly
Phone | Personal phone | For emergencies | Informal | Oral | As needed
Video conferencing | Zoom | For weekly meetings and screen sharing | Informal | Face-to-face | Weekly
Cloud-based document sharing | Google Drive | For online document sharing and team collaboration | Informal | Written | As needed
Notes: For internal communication, team members have agreed to interact using different channels: instant messaging, email, phone, cloud-based document sharing, and video conferencing. Each of which will satisfy a different purpose. From an organization perspective, the communication among team members will be horizontal.
During the project, the day prior to the team’s weekly meeting, the Team Lead will prepare and share the agenda with the talking points to be discussed during the meeting. Team members may add and update items to the agenda if needed.

## Slide 8: Communication
External
Distribution of Information |  |  |  |  | 
Vehicle | Target | Description/ Purpose | Owner | Distribution Vehicle | Frequency
Status Report | Professor | To communicate project progress and to provide deliverables | Project Lead | Written | Every 4 weeks (at the end of each Milestone)
Presentation | Professor | Present project progress and deliverables status | Project Lead | Written | Twice along the project: at week 3 and week 12
Presentation | EVA Instructor & Flight Controller | Present project progress and deliverables status | Project Lead | Written | Every 4 weeks
Notes: The only channel that will be used to communicate with stakeholders will be via Email, and the format that will be used is formal. Dr. Brown will communicate with the team and the team leader with him via email as needed.
The team will provide project liasson and team manager with a report every 4 weeks. Their feedback will be very important to adjust and guide the project in the correct direction.

## Slide 9: Timeline
Project Management for NASA EVA Gamification Phase 2 - Timeline
Notes: The project will be completed using a version of the Waterfall methodology. The project has been broken down into four phases; Initiating, Planning, Executing, and Closing.
Along the entire project development life cycle the project will be tracked, reviewed, and monitored its progress and performance.

## Slide 10: Milestone 1: Initiating
Start Date: May 21, 2018
Completion Date: June 10, 2018
Deliverables:
  Project Charter
  Project Management Plan
  Stakeholder Analysis
  Presentation to Stakeholders

## Slide 11: Milestone 2: Planning
Start Date: June 11, 2018
Completion Date: July 1, 2018
Deliverables:
  Test Plan
  Design Documents
  Requirements
  Updated project documents

## Slide 12: Milestone 3: Executing
Start Date: July 2, 2018
Completion Date: July 22, 2018
Deliverables:
  Project Code
  Initial Testing Results
  Updated project documents

## Slide 13: Milestone 4: Closing
Start Date: July 23, 2018
Completion Date: August 12, 2018
Deliverables:
  Completed Project Code
  Final Testing Results
  Handover Documentation
  Presentation to Stakeholders

## Slide 14: Constraints
The project is bound to the requirement specifications highlighted under the project scope.
The project must be executed within the timeframe under the project schedule.
The actual NASA wiki is not available to the team due to firewalls and access-control mechanisms in place for security purposes.
Notes: The project is bound to the requirement specifications highlighted under the project scope. Additionally, the project must be executed within the timeframe and available team members as shown in the project schedule . The actual NASA wiki is not available to the team due to firewalls and access-control mechanisms in place for security purposes. Consequently, the team has to download and install a local version in order to test.

## Slide 15: Assumptions
The information from the previous phase, in terms of code and documentation, are complete, tested, and working.
The project will be focused on user activity as opposed to Wiki content.
The potential users of the application are:
  Instructors of Astronauts
  Flight controllers
  Astronauts
Notes: The project is a phase 2 project that depends on information from the previous phase 1 project and as such assumes that the code from the previous phase is tested and working, while the documentation is complete and accurate. In addition, the project will be focused on user activity as opposed to Wiki content. The main potential users of the application are namely: instructors of astronauts, flight controllers, and astronauts.

## Slide 16: Risks
The project is dependent on the previous phase for initial code and documentation.
Accuracy of the previous phase code and documentation can have a direct impact on the early stages of phase 2.
Team members availability, experience, and skill level.
Notes: The project is dependent on the previous phase for initial code and documentation. Accuracy of the previous phase code and documentation can have a direct impact on the early stages of phase 2. Team members availability, experience, and skill level can also have an impact on the project’s success. Availability of team members can affect the resources available to execute project, while skill and experience can affect completion time.

## Slide 17: Questions?