## Slide 1
June 11, 2018
Project Name
Project Manager
Period » From:
NASA EVA – Gamification – Phase 2
Dr. Michael Brown
July 1st, 2018
Milestone 2 Commentary:
a) Requirements elicitation -- completed during this phase
b) Design -- developed database design and game design draft documents. Final review of this documents pending.
c) Project Management Plan and Supporting documents -- updated documentation to reflect current status.
Project Team
Risks
Challenges
[C03] Though team’s members roles were distributed during milestone one, it is still a challenge not stepping into each others roles.
>> the team is working hard to overcome this challenge.
[C04] Time constraint: having to deliver all necessary documentation in such short period of time (3 weeks) has been a challenge.
[C05] Define deliverables that can be completed within the stipulated time frame.
#
Status
Open
Open
Close Date
Jul: 09-2018
Jun: 04-2018
Jun: 11-2018
Jun: 18-2018
Jun: 25-2018
Jul: 02-2018
Laura Addiego
– Database lead
Samia Alam
– Quality Analysis lead
Kelli Corey
– Project Management lead
Charles Milk
– Customer Management lead
Adeola Odusola
– Documentation lead
Hung Pham
– Development lead
Owner
 | Very Likely |  |  |  |  | 
 | Likely |  |  |  |  | 
 | Moderate |  | [R03] |  | [R04] | 
 | Unlikely |  |  | [R01] |  | 
 | Rare |  |  |  |  | 
 |  | Low | Minor | Moderate | Major | Extreme
 |  | Impact |  |  |  | 
Probability
Note 1: Showing only active risks.
Note 2: This period’s risks are in bold.
To:
Milestone 3
Design Phase
Milestone 2
R03
Team members getting along and being able to work together.
R04
Time constraint: the final date is rigid and cannot be changed.
Design New Features
100%
Finish Requirements
100%
Database Design
90%
90%
Game Design
90%
Test Plan
Kelli
Kelli
Project Health- Milestone 2
Risk / Issue Description
Created on June 30th, 2018
Open Date
05/25/2018
05/25/2018